## Summary
LMNS Equity and Equality Action Plan: *Insert LMNS Name*
Executive Summary | Provide an executive summary of the equity plan and the key themes identified for progression.
Action Plan Contents | 1. Vision, Values & Aims
2. Detailed Action Plan
3. Population
4. Co-Production
5. Roles & Responsibilities
6. Resources
7. Communication Plan
8. Measurement Plan
9. Sustainability

## Vision
Vision
Overall Vision | BNSSG LMNS will work with system partners and women and their families to design and deliver inclusive, supportive and safe services across maternity and neonatology.
Values | Value | Rationale | Key Actions
| List the values that underpin the equity strategy | Why is this value important? | What are the key actions that align with this action? (from 'Key Actions' tab)
Develop further once ICS values, aims etc. developed and published following the Big Conversation https://junglegreen.researchfeedback.net/s/tdsfh
Aims | List the key aims of the equity strategy, which should align with any ICS aims relating to health inequalities
Please see detailed action plan
ICS Interdependencies | Perinatal mental health
Diabetes
Population health management
Workforce

## Detailed Action Plan
Detailed Action Plan
No. | Action | Detail | Key Milestones | Target Date | Metrics for Success | Comments/Updates
| Provide a summary of the action identified (make sure this is SMART) | Detail the action and the exact steps required to achieve it in the given timeframe | What are the key milestones to success? | When will the action be completed? | List the relevant metrics for measuring the success of the action | Comments/Updates
1 | To conduct population health management analysis on (BMI, smoking, late booking, Mental health, ethnicity, age, deprivation) to identify target population. | Population health management analysis (BMI, smoking, late booking, mental health, ethnicity, age, deprivation) - Primary Care Network (PCN) on women recently pregnant to identify which cohorts of target population to focus on interventions. | Share population health findings with Task and Finish Group and LMS delivery board. | 05/05/2022 and 20/5/22 | Collection of qualitative feedback from Task and Finish Group and LMS delivery board. | Identified four priority PCNs for BNSSG - Phase 1 • Bristol Inner City PCN (Lawrence Hill and Bristol central Wards) - BMI, late booking, MH, ethnicity, Deprivation, age) Pier PCN (Weston Super mare South) (BMI, MH, deprivation, smoking) Phase 2 • Swift PCN (Hartcliffe and Withywood Wards) -BMI, smoking, MH, Deprivation, age) . Network 4 PCN (New Cheltenham) - smoking, BMI *This has now been completed
2 | To map community midwifery and health visiting teams with geographical areas identified | Map teams to PCNs and MSOAs identified in PHM analysis | Identify individuals and teams in each of the phase one and phase two target areas | 2022-06-01 | List of groups of women with relevant community midwifery and health visiting teams and PCNs | Complete
3 | Audit late bookers | Audit late bookers to understand scale of issue and if there are any identifiable themes or demographics. | Audit of late bookers | 2022-08-01 | Number and demographics of late bookers | PHM analysis carried out on late bookers and demographics largely match communities already identified. Also identified proportion are classed as late bookers as moved into area
4 | To conduct meetings/events with community assets to overcome potential barriers to accessing perinatal mental health services. | 1. Conduct meetings with ICB Mental Health project manager to tie in current work with equity action plan. 2.Engage with current networks and identify new connections to support the project including those who hold prominent positions within the community and likely to be held in high regard by other residents to build and develop relationships and to discuss how to overcome barriers to accessing perinatal mental health services for e.g. CAAFI, Mothers for Mothers, Vintage Community Church- Weston-Super-Mare Church of The Nazarene, Bristol Somali Resource Centre, Project mama, Nilaari 2. Discuss with community leaders/organisations how they would like to receive feedback from survey findings. | Meetings held with organisations/community assets. | 31st October 2022 | Collection of data from diverse service users in partnership with local organisation to shape maternity services. | Complete
5 | Provision of continuity of carer focussing on IMD1 and Black, Asian and minority ethnicity women | 1. Putting in place the building blocks to deliver MCoC as the default model when safe staffing allows | 1. Following birthrate assessment and agreement of plans by LMNS and Trust boards to fulfil safer staffing requirements before reimplementation of plan. | TBC | Number of women from the identified groups receiving MCoC | Currently paused as per Ockenden guidance. Juniper team set up under UHBW, NBT currently exploring MCoC model for 'vulnerable' population as part of their EDI workstream
6 | Community asset mapping | Completed as part of stage one
7 | Develop the role of the EDI PEF to support staff in the provision of care to women/birthing people with protected characteristics | 1. Trial at UHBW of a part time PEF in this role | 1. Review funding for this role 2. Link with EDI leads in each trust | 2023-03-01 | .Improvement in cultural competency awareness for staff | EDI Pef role established under UHBW, not currently at NBT, something to poss explore as part of the current EDI Workstream?
8 | Black Maternity Matters a collaborative pilot project for midwives and maternity support workers to reduce the inequitable outcomes faced by Black mothers and birthing people | 1. 2 midwives working across BNSSG championing the needs of women in this group 2.15 participants attending training and workshops 3. Identifying needs following work with parent partners and focus groups | 1. Focus groups to identify issues 2. Increase profile in both trusts with communication in leadership meetings 3. Poster campaign to educate staff around speech/phrases | 2024-12-01 | Evaluation of pilot by WEAHSN with a view to rolling out if achieves objectives Monitor feedback from women | Currently about to launch cohort 3 training and education group- to continue as part of long term stategy (hopefully)
9 | Review and implementation of personalised care and support plans | 1. Co-produced with women from diverse backgrounds 2.Produced to the required national standards 3. Review once used through entire pregnancy journey | 1. Agreed via LMNS 2. To be agreed via both trust governance bodies 3.Establish training and launch plan 4.If at review the PCSP is deemed successful, look at translation to languages most used for translation 5. Incorporate into digital format with new system | 2024-08-01 | Audit document with users once been used through pregnancy journey and regular audit of use | Initially paused as originally launch during Covid pandemic, reviewed original publication and 2nd addition relaunched Sept 22. Has currently gone paperless with intoduction to BN, Audit due to commence Mid Feb on use of PCSP by women and review effectiveness of digital copies. Consider re introducing paper version following evaluation of audit.
10 | Implementation of the perinatal pelvic health project | 1.Implementation of the agreed project plan over a 3 yr period 2. Analysis of needs and gaps in service | 1. Focus groups in areas with a high ratio of black, Asian and minority ethnicity and IMD1 women 2.Videos created 3. Translation of advice media to languages most translated within BNSSG | 2024-09-01 |  | video's have been created and are on website, fully translatable in 11 languages (on the site) and 5 (most spoken) languages for the videos.
11 | Continue to improve smokefree pregnancy pathways including engagement and outcomes | Review effectiveness of service to date and identify areas for improvement | Recruit smokefree pregnancy midwife to lead BNSSG service | 2023-01-01
12 | Incorporating service user feedback into service improvement plans | Review feedback received to date (mental health, BAME, CoC pathway etc.) | Include feedback at service delivery level | Ongoing |  | Current MNVP AN education survey completed and PCSP audit currently underway.
13 | Join up and enhance the services delivered via transformed Family Hubs (Bristol). | Bristol received Family Hubs and Start for Life programme funding package for 2022–2025. Funded workstreams include infant feeding and perinatal mental health and parent-infant relationships and parenting support. | Local needs assessment, open family hubs within first half of 2023, establish parent carer panel by April 2023, publish Start for Life offer | 2025-04-01 | Funding is contingent on reporting against milestones and KPIs as set out by the government. | Governance model developed, multi-agency steering group established, multi-agency locality focus groups held. Co-design planned with stakeholders, including local families.
14 | BMI; Healthy weight conversations skills training delivered to staff from health visiting and midwifery | Complete | Complete | 2022-05-01 | KPIs on outputs (number of staff trained, sessions delivered etc), quality of training and outcomes (increase in knowledge, skills, confidence). Long term evaluation being carried out | 199 staff were trained in total, KPIs regarding quality and outcomes were achieved.
15 | BMI: Develop a community asset-based approach to healthy weight | BeeZee Bodies commissioned by Public Health (Bristol only) to carry out insight work to inform an asset-based community development approach to healthy weight. Focus is on seldom heard populations from diverse ethnical backgrounds. The learning phase will inform future commissioning intentions. | No budget for future commissioning, but will be working collaboratively with Locality Partnerships and partners across the system to look at asset building with communities | 2023-06-01 | Collection of qualitative feedback from staff, service users and community organisations. | An initial insights report was shared in Jan 2022. Details insights and a workshop with partners on how to support healthy weight is planned for Nov 9th 2022. Work is currently ongoing
16 | Improve equity of access and increased referrals to Bristol Breastfeeding Support Service. This is a targeted service in deprived wards in Bristol with low prevalence for breastfeeding | 1. Re-draft SOP to clarify data sharing and processes 2. Draft a short script for midwives 3. Promotion of service and clarification of referral process to MW teams 4. Explore if Children's Centres can have information about pregnant women to provide antenatal | 1. SOP redrafted. 2. Scrip drafted. 3. Promotion of service to teams. | Ongoing | Referral data
17 | Ensure equity of access to postpartum contraception for women across BNSSG by rolling this out as universal offer. | 1. Employ project manager. 2. Develop and commence training packages. 3. Develop follow up and complex care pathways. 4. Purchase stock and equipment. 5. promote service. 6. Ensure have evidence based, accessible resources for women. 7. Service evaluation |  | 2024-08-01 | Outcomes and output data e.g. patient experience, prescription data, staff trained etc | Pilot went live Oct 23, due for 6/12 evaluation shortly.

## Population
Population
Population Needs Analysis | 16% of BNSSG residents live in areas that are amongst the 10% most deprived in England, with the majority of these in Bristol. In BNSSG, women under 20 and over 40, Black, Asian and Mixed Ethnicity women and women living in deprived areas are most likely to experience poor birth outcomes (premature births, still births, low birth weight). Black women experience the highest prevalence of poor outcomes relative to women from other ethnic groups. Whilst, women living in the most deprived areas experience the highest prevalence of poor birth outcomes overall. Bristol’s population is ethnically diverse, with 16% of residents from Black, Asian and Mixed Ethnicity groups.
Overview of Local Data | NHS BNSSG CCG (2021), Annual Report, JSNA (BNSSG), English Indices of Deprivation, MSDS, Maternal Health Equity Audit,
System Wide Data set aggregated to Primary Care Network (PCN) level and (Middle layer Super Output Area) MSOA level
| Population Health Management | .
Key Targets Identified | The BNSSG Maternity Health Equity Audit (HEA) released in November 2021 looked at maternal risk factors and identified cohorts who are most likely to experience them. These include: smoking and late booking in 20-24 year olds; late booking and BMI in Black women; smoking, BMI in Mixed Ethnicity women; smoking and BMI in White women; and late booking, BMI, and smoking in women living in deprived areas. The HEA also identified cohorts likely to experience poor birth outcomes – deprivation, ethnicity, age were all identified as having an effect on outcomes such as premature births, low birth weight and still births.
Comments | The BNSSG region is a large, complex area with both urban and rural populations. The total population is 969,256 (465,866 in Bristol, 215,572 in North Sommerset and 287,816 in South Gloucestershire). There are two maternity providers, North Bristol Trust NBT) and University Hospitals Bristol and Weston NHS Foundation (UHBW). There were 10,182 live birth registered across BNSSSG in 2020 - Bristol 5,270 (52%), North Sommerset 3,002 (19%) and South Gloucestershire (29%). We currently have 44,124 women of childbearing age between 15-44 years old.

## Co-Production
Co-Production & Engagement
Use this power/impact matrix to consider how to get the best from your co-production and engagement activities:
| Low Impact |  | High Impact
High Power | e.g. Inform, engage |  | e.g. Inform, involve, co-produce, engage, empower
Low Power | e.g. Inform |  | e.g. Inform, involve, co-produce, engage
Consider existing relationships or projects involving co-production, and how these might link to your equity aims |  | Project |  | Relevance to equity aims | Contact | Next Steps
|  | CAAFI Health |  | Reducing inequalities for Black, Asian and Minoristised communities for e.g., BMI, perinatal mental health - support with gathering local patient feedback | Huda Hajinur | Continue working relationships
|  | The Bereavement Somali Project |  | Support with gathering views to shape maternity services. | Lisa Kirk | Continue working relationships
|  | Bluebell maternal mental health |  | Engage with wide range of women experiencing mentla health issues | Ruth Jackson | Continue working relationships
|  | Black Maternity Matters QI Project |  | Supporting midwives to reduce the inequitable maternity outcomes for black mothers. | Ann Remmers | Continue working relationships
|  | Smokefree pregnancy early implementer site |  | Working to reduce smoking rates in pregnancy and in wider life | Kate Grant | Continue working relationships
|  | Green prescribing projects such as Mother Nature |  | Supporting women from a wide range of backgrounds | Steve Spiers | Continue working relationships
|  | Existing BAME staff networks |  | Working with wide range of BAME staff | Terri Gnani | Continue working relationships
Plan how the actions you identified in the detailed action plan will be meaningfully co-produced |  | Action |  | Opportunities for co-production | Lead | Resources/support needed | Next steps
|  | To develop questionnaire on key health priorities identified by Health Equality Audit and population health management analysis. |  | Work with Task and Finish Group, third sector and statutory organisations, BNSSG EDI leads, West of England Academic Health Science Network Insight and Engagement to design questionnaire and ensure it is suitable and culturally appropriate for a diverse range of women in deprived area and Black, Asian and Mixed Ethnicity groups.. | Project Manager | Data on local population groups, support from Task and Finish Group, Young mothers rep. Black Mothers Matter and BNSSG EDI leads. West of England Academic Health Science Network co-production knowledge. | Contact Black Mothers Matter, Young person's representation at Meriton to pilot questionnaire, Contact Insight and engagement, EDI leads and West of England Academic Health Science Network to arrange meetings to design and finalise questionnaire.
|  | To produce poster to encourage community engagement and participation of service users. |  | Work with Black, Asian and Mixed Ethnicity service users, EDI lead, MVP to design content and ensure culturally appropriate. | Project Manager | Data on local population groups, support from EDI lead and MVPs. Insight and Engagement. | Contact service user to organise co production meeting with MVP lead. Contact insight and engagement for multilanguage access statement and develop poster
|  | To engage with maternity and neonatology staff including Black, Asian and minoristised Ethnic maternity staff forum to solicit views on WRES data. |  | Work with BNSSG EDI lead, Black .Asian and Mixed Ethnicity maternity staff forum and Task and finish group to ensure data necessary is gathered for baseline. | Project Manager | Workforce Race Equality Standard (WRES) data. Support from Black, Asian and Mixed Ethnicity maternity staff forum, Support from LMS leads to engage with North Bristol Trust (NBT) and United Hospital BW maternity staff. | Contact Black Asian and Mixed Ethnicity forum and EDI leads to create an action plan based on the WRES data. Arrange meetings with LMS leads to engage maternity staff.
|  | Conduct meetings with MVP and Healthwatch to partner with and solicit feedback from existing service user, patient and community groups on key priorities (BMI, late booking, smoking, mental health) |  | Work with Healthwatch to ensure diverse range of service users/patient voices and community groups in Phase 1 and Phase 2. Phase 1 • Bristol Inner City PCN (Lawrence Hill and Bristol central Wards) - BMI, late booking, MH, ethnicity, Deprivation, age) Pier PCN (Weston Super mare South) (BMI, MH, deprivation, smoking) Phase 2 • Swift PCN (Hartcliffe and Withywood Wards) -BMI, smokng, MH, Deprivation, age) . Network 4 PCN (New Cheltenham) - smoking, BMI | Project Manager | Presentation on Equity and Equality project to share vision, purpose and priorities identified in BNSSG. | Contact health watch to organise meetings and service user events.
|  | To conduct meetings to feedback survey findings to service users, community organisations,MVP, Healthwatch and staff. |  | Work with Healthwatch, service users and community organisations to ensure findings/ recommendations are prioritised and the way forward agreed in shaping maternity services. | Project Manager | Presentation/report on Findings. | Book meeting dates and times to feedback findings from survey to staff, Healthwatch, service users, community organisations and social media platforms.

## Roles & Responsibilities
Roles & Responsibilities
| Role | Respsonsible For | Name | Comments
| What is their role? | What are their responsibilities in relation to delivery of the action plan? Link back to to detailed action plan. | Name | Comments
| Advanced Nurse Practitioner | Value and Population Health, BNSSG CCG to ensure target population for interventions | Anne Wray
| Insights and Engagement Officer | 1. Ensure service user questionnaire and leaflets meets requirement and standard. Help designing, uploading and analysing a survey, support running events or focus groups, and support from the comms team with designing campaign materials or sharing messaging. | Fritha Voaden
| BNSSG Inclusion Coordinator | Oversight of ICS responsibility for addressing health inequalities within local system, link to ICS aims | Sharon Woma
| Black Mothers Matter | Ensuring service user involvement and meaningful co-production. Pilot questionnaire | Sonah Paton
| HealthWatch | Ensuring service user involvement across BNSSG and meaningful co-production as health and social care champion . | Julie Bird Stephen Watters Helen West
| MVP Lead | Ensuring meaningful co-production of every aspect of the action plan. | Laura Cousins
| Support for Young Parents | Ensuring meaningful co-production for young parents. | Jules Cook | The Meriton
| Bristol Breastfeeding Support Team Lead | Ensuring meaningful co-production with women in deprived area. | Sandra Tanner
| Infant Feeding Midwives | Infant feeding | Marion Copeland
| Infant Feeding Specialist Health Visitor | Infant feeding | Katharine Curren
| GP Asylum Seekers and Refugees | Ensuring meaningful co-production with refugees and asylum seekers. | Dr Carloline Crenstil
| Interim Equality, Diversity & Inclusion Manager | Ensuring an Equality Diversity and Inclusion lens for targetted women in the action plan to promote good relations and practices towards different minority groups. | Charlotte Nicol
| Maternal and Neonatal Clinical Lead, WEAHSN | Ensure work collaboratively with Black Mothers Project. | Ann Remmers
| Project Manager (in post December 21 - June 22) | Ensuring project runs smoothly and meets timescales and deadlines. Working with cultural organisations, staff and communities to ensure co-production is meaningful | Charmaine Lynch
| LMNS clinical lead midwife for UHBW | Support links and engagement with University Hospital Bristol and Weston (UHBW) maternity staff. | Terri Gnani
| LMNS clinical lead midwife for NBT | Support links and engagement with North Bristol Trust (NBT) maternity staff. | Ami George
M | Head of Equality, Diversity & Inclusion - NBT and Bristol Women’s Commission Co-chair Health Task Group | Ensuring Health inequality agenda is prioritised. | Monira Ahmed Chowdhury
| Patient experience lead | Ensuring the voice of patient experience for women and children NBT | Clare Ridler
| Programme Lead | Oversight of project | Alex Layard
| Programme Manager | Project lead | Suzanne Cheng
| Perinatal Mental health Project Manager | Project manager for maternal mental health | Leah Pearson
| Green prescribing lead | Green prescribing pilot projects | Steve Spiers

## Resources
Resources
Total Funding Allocated | Total amount allocated from Maternity Transformation, and any other relevant funding sources.
Detailed Budget | Item Description | Unit Price (£) | Quantity | Total (£) | Details/Comments | Actual Expenditure (£)
| Supervisory Band 7 (37.5 hours) |  |  | 27732.5 |  | 23110.42
| Black Maternity Matters Midwife Champion |  |  | 5815 |  | 4845.83
| Black Maternity Matters WEAHSN project |  |  | 15398 |  | 12831.67
| Black Maternity Matters Study Day |  |  | 2040 |  | 2040
| BaME / Equity - business intelligence |  |  | 23015 | Need top identify where resource best allocated e.g. provider BI teams
| Equity and Equality - Project Officer B6 |  |  | 45000 | Recruitment underway to replace B7 PM
| Equity and Equality - Co production |  |  | 40000 | Working with Healthwatch to allocate funds
| Perinatal MH |  |  | 56000 |  | 23333.33
| Maternity Voices Partnership |  |  | 26500 |  | 11041.67
| SDF Tobacco - Maternity |  |  | 132000 |  | 55000
|  |  | Total/Actual Cost (£) | 373500.5 |  | 132202.92

## Communication Plan
Communications Plan
Subject | Key Messages | Audience | Format/Platform? | Target Date(s) | Comments
What subject do the communication(s) relate to? | What are the key messages? | Who are the desired audience? | What format will the communication(s) take? Where will they be shared? | When will the communication(s) be circulated/shared? | Comments
e.g. Awareness of equity and equality analysis and action plan | What is the quality and equality action plan? What has the LMNS done so far to address health inequalities? What is the action plan? How has the action plan been co-produced with women and families? | CCG, acute and primary care providers, women and families, local communities | Email newsletters, social media posts, posters, leaflets | 2022-09-01 | Summary sheet to be prepared and circulated via suggested formats
Full communication and engagement plan being developed and includes the related elements included on the 'detailed action plan' worksheet

## Measurement Plan
Measurement Plan
Measure | Detail | Type of Measure | Data Collection | Existing Source or New Data Collection? | Comments
What is the success measure? | Provide detail on the measure and how it is relevant to the action plan | Is this an outcome or process measure? | How will data be collected to demonstrate this measure? |  | Comments
E.g. Number of women from black and Asian populations on a continuity of carer pathway |  | Outcome | Downloaded from the National Maternity Services Dashboard | Existing source
Full measurement plan being developed and includes the related elements included on the 'detailed action plan' worksheet |  |  |  | Existing source
Number of pregnant women who smoke |  | Process | SATOB and SATOD, MSDS if available | Existing source
Number of women with a BMI >30 |  | Process | BMI, MSDS if available | Existing source
Number of women with diagnosed mental health issues |  | Process | Mental health field on EPR, MSDS if available | Existing source
Number of women who are late bookers |  | Process | To be defined, booking date and dating scan on MSDS | Existing source
Number of women from IMD1 |  | Process | MSDS, SUS | Existing source
Mumber of BAME women |  | Process | MSDS, SUS | Existing source
Number of BAME staff in maternity and neonatology |  | Process | WRES, provider ESR | Existing source

## Sustainability
Sustainability and Embedding Plan
Action | Current State | Resources Needed | Who needs to be involved to achieve sustainability? | How will you know it is embedded? | Timescales and Evaluation
Which action does this relate to? | What is the current state of the action, how has it improved things? | What resources are needed to embed this action into 'business as usual'? | Who needs to be involved to embed this action and make it sustainable? | How will you know that this action is embedded and is 'business as usual'? | What are the timescales for embedding this action? How will it be evaluated?
e.g. All patient information to be culturally competent and translated into multiple languages. | Patient information has passed cultural competency assessment following development with service users, and is available in 5 languages. | Funding to reimburse service users for monthly review sessions for new and existing patient information | Trust equality leads, trust communications teams, service user engagement groups | All patient information reviewed by service users on a regular basis | 12 months, annual audit of patient information